## INSTRUCTIONS
Instructions for Planning Level Cost Estimating Tool for Bicycle Infrastructure Projects
The bicycle project cost estimator is designed to be an 'easy to use' tool. Users enter a few parameters for the intended project and the tool calculates costs based on construction costs and assumed contingencies for design and construction. These INSTRUCTIONS provide basic steps on how to use the tool. Additional guidance is provided in each tabs.
1. Review the Introduction and the Table of Contents. Select the type of bikeway that is most similar to your project and go to that spreadsheet tab to estimate the cost of your project.
2. Each spreadsheet tab has Instructions on the right side of the cost table. The instructions will explain what to fill in and how the costs are calculated automatically for each row.
3. ONLY fill in the orange or blue cells. The other cells will auto-populate and auto-calculate.
4. The tab named 'Master List of Items' provides the costs for the current year and those costs automatically link to the unit costs in each bikeway tab. It provides a little more detail on how the unit costs were chosen. In general, do not change these unit costs. However, if you have a non-standard item, this may provide some details on the unit costs so you can prorate them for your project.
5. The contingencies for Maintenance of Traffic/Mobilization, Construction, and Design/Permitting have been predetermined for each type of bikeway using engineering judgement. MDOT does not recommend reducing these contingencies; however, they could be increased if the complexity of the project warrants it.
Updated: August 2026.

## Introduction
Introduction for Planning Level Cost Estimating Tool for Bicycle Infrastructure Projects
1. This planning level cost estimating tool was initially developed by the Maryland Department of Transportation and the Baltimore Regional Transportation Board's Bicycle and Pedestrian Advisory Group. The purpose of this estimator is to provide guidance to local jurisdictions on project design and construction costs associated with bicycle infrastructure. Cost estimates within this tool are developed by identifying pay items and establishing generalized quantities. This tool aims to cover a wide range of possible expenses that are typically incurred with bicycle projects, but cannot account for all possible items. To account for increased costs as design progresses, a 30% contingency is included to allow for items not yet designed. The cost estimator is also provided as a general planning tool to compare costs from planning, develpoment and engineering professionals.
2. The cost estimating tool is based on American Association of State Highway Transportation Officials (AASHTO) and Maryland Manual of Uniformed Traffic Control Devices (MDMUTCD) standards for facility design, pavement markings, sign placement and other standards. The standards are incorporated into quantity calculations based on the project length and other user preferences. Cost sources are provided in the MASTER LIST OF ITEMS whenever possible.
3. The cost estimating tool is incorporates quantity formulas based on the project specifics. Users only need to input data into the orange or blue fields (project length, the number of intersections and average intersction width) to calcuate many of the costs.
4. As no two bicycle facilities are exactly alike, this tool is divided into bicycle facility types to allow for more accurate estimates. Each facility type is located on separate tabs. The below TABLE OF CONTENTS list varying bicycle facilities and descriptions to help identify the appropriate facility to use.
5. Note that this estimator includes generalized costs for asphalt, concrete, grading, drainage improvements, limited utility relocation, pavement markings, signs and traffic signal adjustments. The estimate does not include construction management, special site remediation or the cost for ongoing maintenance. A cost range has been assigned to some general categories; however, these costs can vary widely depending on the exact details and nature of the work. The overall estimates are intended to be general and used for planning purposes. Construction costs will vary based on the ultimate project scope, implementation schedule, and economic conditions at the time of construction.
Additional Costs Associated with Construction Projects
1. In addition to design and construction costs, various costs are associated with capital project preparation. These costs include preparing environmental documentation, performing a hydrologic and hydraulic study and establishing easements or acquiring properties, identifying historic or cultural resources, endangered species or contaminated site remediation.
2. For shared-use path projects that include lighting, coordination for the installation, maintenance, operation and expenditure needs to be coordinated among stakeholders. Metering and billing are critical items which need to be determined prior to the lighting design.
3. Planning level cost estimates aim to cover a wide range of possible expenses that are typically incurred with projects, but cannot account for all possible items. The cost estimator is also provided as a general planning tool to compare costs from planning, development and engineering professionals.

## Table of Contents
Table of Contents Planning Level Cost Estimating Tool for Bicycle Infrastructure Projects
Bicycle Facility Type | Tab Name | Description
Shared Lane | Shared Lane | A shared lane is represented by conditions where bicycle traffic shares a travel lane with motor vehicle traffic. While a shared lane is not a dedicated bicycle facility, the tab accounts for shared lane markings, also known as sharrows, and related signage for ONE or BOTH travel directions.
Bike Lane | Bike Lane Curbside | A bike lane is a 5-foot-wide area on the roadway delineated by two parallel white pavement markings. Bike lanes can be against the curb or between a row of parked cars and a motor vehicle travel lane. This tab can be used where the bike lane is against the curb, WITHOUT on-street parking, on ONE or BOTH sides of the street. It assumes no roadway widening, only reallocating the existing pavement width.
Bike Lane | Bike Lane with Parking | A bike lane is a 5-foot-wide area on the roadway delineated by two parallel white pavement markings. Bike lanes can be against the curb or between a row of parked cars and a motor vehicle travel lane. This tab can be used where the bike lane is against the curb, WITH on-street parking, on ONE or BOTH sides of the street. It assumes no roadway widening, only reallocating the existing pavement width.
Buffered Bike Lane | Buffer Bike Lane Curbside | A bike lane can be separated from motor vehicle travel lanes by a striped buffer. The buffer allows for additional roadway space between bicycle traffic and motor vehicle traffic. Buffers are at least three-feet-wide and may have vertical delineators, such as flex posts, bollards or planters, to provide additional definition to the bicycle area of travel. The buffer includes white parallel lines along both sides of it. This tab accounts for buffered bike lane construction on ONE or BOTH sides of a roadway. While buffered bike lanes may be located between a row of on-street parking and a motor vehicle travel lane, this configuration allows motor vehicle traffic to encroach on the bicycle area of travel, thus reducing the safety of the bike facility. Due to diminished safety, this estimator does not include calculations for buffered bike lanes between parked vehicles and motor vehicle travel lanes.
Protected Two-way Bike Lane or Cycletrack | Protected Two-way Bike Lane | A protected bike lane is bike lane that has a physical barrier between the bike lane and motor vehicle travel lane. For a single direction protected bike lane, use the BUFFER BIKE LANE CURBSIDE tab. Use this tab for a two-way protected bike lane where two opposing direction bike lanes are located against the curb on one side of the roadway.
Bicycle Boulevard/ Neighborhood Greenway | Bike Boulevard | A bicycle boulevard, or neighborhood greenway, is a low-traffic-volume, low-traffic-speed roadway with minor roadway adjustments to improve bicycle access. Typically, traffic calming features are applied to a residential corridor to reduce motor vehicle speed and access. This tab includes a variety of traffic calming features that may be included, or excluded. As most bicycle boulevards are on two-way residential roadways, this tab includes information that reflect those conditions; however, it also includes an option for a contraflow bicycle lane, where a double yellow line separates the contraflow bicycle lane.
Shared-use Paths/Paved Trails | Shared-Use Paths | A shared-use path is a two-way, hard surface trail that can be used by both bicyclists and pedestrians. Most shared-use paths have an independent alignment and include most construction items associated with new roadway construction.
Complete Streets Intersection Treatements | Complete Sts Intersection | A complete streets intersection is designed for the safety of all users, including pedestrians and bicyclists. This includes temporary treatments, traffic calming, bicycle treatments, and pedestrain safety benefits.

## Master List of Items
Directions for Updating Unit Costs Annually for Inflation
1. Enter the Original Year of the Base Unit Costs and the Current Year. The number of years to inflate will auto populate. (RED NUMBERS in table below) 2. Enter the average annual inflation rate over the past few years. (RED NUMBERS in table below) 3. The compounded inflation rate will automatically calculate and be applied to the Base Unit Costs to obtain the Inflated Unit Costs in the table below. 4. The inflated unit costs will automatically update throughout the spreadsheet tabs. 5. Enter the Unit Costs for the Base Year - only enter costs in the ORANGE cells.
Original Year of Base Unit Cost = | 2026 |  | Compounded Inflation = |  | 100%
Current Year = | 2026
Annual Inflation Rate = | 3.5%
Number of Years to Inflate Unit Costs = | 0
MASTER LIST OF ITEMS
Items | Unit | Dimensions | Base Unit Cost for Year: | Inflated Unit Cost to Year: | Source for Unit Costs
|  | (if applicable) | 2026 | 2026 | (SHA 2026 Cost Estimating Manual [CEM])
Pavement Markings
Shared Lanes symbols | Each |  | 300 | 300 | SHA Price Index Jan 2026. Item #549622. MD Standard #550.01. 9.0 SF for each. $33/SF
Bike Lane symbols | Each |  | 300 | 300 | SHA Price Index Jan 2026. Item #549624. MD Standard #550.01. 10.0 SF for symbol+arrow. $33/SF
5" White Retroreflective Pavement Marking | Linear Feet |  | 5 | 5 | Page F-24 CEM for Inlaid Tape
5" White Retroreflective Pavement Marking for Lane Lines (3' Buffer, 10' Spacing) | Linear Feet |  | 1.25 | 1.25 | Page F-24 CEM for Inlaid Tape
5" Yellow Retroreflective Pavement Marking | Linear Feet |  | 5 | 5 | Page F-24 CEM for Inlaid Tape
Green Thermoplastic Pavement Marking | Square Foot |  | 20 | 20 | Page F-24 for thermoplastic and unit cost from NCDOT TAP cost estimates
Pavement Resurfacing
Fine/Micro Milling Existing Pavement Markings Only (no resurfacing) | Square Yard |  | 6 | 6 | SHA Price Index Jan 2026. Item #508012 or #508017. MD Standard #508.
Milling of Asphalt Pavement (up to 1") | Square Yard |  | 5 | 5 | SHA Price Index Jan 2026. Item #508010 or #508012. MD Standard 508
Resurface 1" Hot Mix Asphalt for Roadway | Ton |  | 130 | 130 | SHA Price Index Jan 2026. Item #504500.
Signs | Square Footage (not used for cost) | Dimensions (not used for cost) | Each | Per SF
R3-17 (Bike Lane) | 3 | 24" x 18" | 500 | 500 | Page F-25 CEM
Rd-17aP (Bike Lane Ahead) | 1.3333 | 24" x 8" | 500 | 500 | Page F-25 CEM
Rd-17bP (Bike Lane Ends) | 1.3333 | 24" x 8" | 500 | 500 | Page F-25 CEM
R4-4 (Right Turn Yield to Bikes) | 7.5 | 36" x 30" | 500 | 500 | Page F-25 CEM
R4-11 (Bikes May Use Full Lane) | 6.25 | 30" x 30" | 500 | 500 | Page F-25 CEM
D11-1 (Bike Route) | 3 | 24" x 18" | 500 | 500 | Page F-25 CEM
Wayfinding Signing | Varies | Varies | 2000 | 2000 | Assume larger, unique sign will cost more
Separation
Flex posts (10' spacing) for contraflow or additional lane | Each |  | 225 | 225 | VDOT's bid tabs for 2025-026.
Low profile, pre-fab concrete barrier (10' length). Either continuous or spaced 10' apart | Each |  | 400 | 400 | Used SHA Standard Wheel Stops, #634415. They are 7 feet long so cost was prorated for 10-foot length and increased for non-standard item.
Concrete Planters (approx. 6' length, 25' spacing) | Each |  | 2300 | 2300
Raised Concrete Median | Linear Feet |  | 250 | 250 | SHA Price Index, multiple years.
Signalization
New Bicycle Signal Heads on Existing Signal Poles (incl. heads, wiring, conduit, new or upgraded controller) | Per Crossing |  | 20000 | 20000
New Small Traffic Signals for Designated Bicycle Lane or Separate Facility (including heads, poles, push-buttons, wiring, conduit, new or upgraded controller) | Per Crossing |  | 30000 | 30000
New Pedestrian Signal Heads on Existing Signal Poles (including heads, push-buttons, accessible ped signals, wiring, conduit, new or upgraded controller) | Per Crossing |  | 20000 | 20000
Traffic Calming Features
Curb Extensions | Each |  | 22000 | 22000 | NCDOT TAP Cost Estimates and Portland, OR Study of Costs and FHWA Study. Inflated from 2013.
Landscaped Chicanes | Each |  | 30000 | 30000 | Assume 30-35% higher than curb extensions due to landscaping. From NCDOT TAP Costs.
Raised Crosswalk | Each |  | 13000 | 13000 | Portland, OR Study of Costs and FHWA Study. Inflated from 2013
Raised Intersection | Each |  | 100000 | 100000 | FHWA Study. Inflated from 2013. Assume it is small to moderate sized intersection.
Mini-Roundabout | Per Intersection |  | $60,000 to $250,000 | $60,000 to $250,000 | This is wide range of costs. Local jurisdiction to choose cost based on how complicated new mini-roundabout would be. Low end is mini-roundabout on simple neighborhood street. High end is larger or has more potential conflicts, but still falls predominently within the existing right-of-way.
Pedestrian Refuge Islands | Each |  | 7000 | 7000 | Assume 6' wide and 30' long. Preferred width 8-10' and preferred length 40'. If 40-feet long, add $2000/EA. If 10' wide, add $2000/EA.
Bicycle-friendly speed humps | Each |  | 5000 | 5000 | Used FHWA Study from 2013 and VDOT's Bidtabs from 2025.
Additional Features
Bicycle-friendly storm grates | Each |  | 1000 | 1000 | NCDOT TAP Cost Estimates inflated from 2024 to 2026
Shared Bus Boarding Areas/Islands - Concrete Island | LF of island (add length for adjacent ramps and tapers at ends) |  | 250 | 250 | Cost is based on length. Assume 9' wide. Cost based on curb & gutter $100/LF and sidewalk due to width $150/LF. Total = $250/LF PLUS $3300
Shared Bus Boarding Areas/Islands - Modular Island | Each |  | 37000 | 37000 | Estimated cost based on sample brand of modular island for 6'widx40'long boarding area, 6'x6' connection for ramp, 2 ramps, short connection to sdwk.
Structures
Retaining Wall | Square Foot |  | 295 | 295 | Used 2022 CEM for SF cost of $260 for cast in place. [2026 CEM did not have SF cost]. Inflated to 2026.
Bridge | Square Foot |  | 472.5 | 472.5 | New or replacement steel girders carrying 1 road over another road. Because this is full roadway bridge, CEM cost reduced by 10%. Page F-17 CEM.
Pre-fabricated Bridge | Square Foot |  | 250 | 250 | Estimate $150-$350/SF for bridge and installation.
Boardwalk (with railings) | Square Foot |  | 125 | 125
Boardwalk (without railings, close to ground) | Square Foot |  | 90 | 90
Tunnel | Square Foot |  | 2500 | 2500
Lighting | Per Pole |  | 11000 | 11000 | Page F-23 CEM
Railroad Protection
Fencing (6-feet tall) between Railroad and Path | Linear Feet |  | 45 | 45 | SHA Price Index Jan 2026. Item #690124.
RR Crossing Monitoring during Construction | Each Location |  | 750000 | 750000
Shared Use Path
Shared Use Path (10' wide) | Per Mile |  | 1800000 | 1800000 | VDOT Table for SUPs and comparison with trail in NH.
Contingencies and Additives
Maintenance of Traffic & Mobilization | Percentage of Subtotal of Costs |  | This is typically percentage of categories 2, 4, 5, and 6 as follows: - 40% for construction completed under area-wide or IDIQ contract - 65% for project being advertised as stand-alone contract - Some judgement is necessary because quantities are for traffic-related items and not 2, 4, 5, and 6 - Judgement also necessary for facilities that have limited interactions with roadway lanes. HCEM 2026, page F-14
Contingency | Percentage of Construction Subtotal, including MOT-Mobilization |  | Per HCEM 2026, Page F-3. Some judgement is necessary based on how much detail has been completed before cost estimate is prepared. - New Start to Alternatives Meeting - 40% to 35% - Alternatives Meeting to Last Cost-per-mile Estimate-35% to 30% - 1st Detailed Estimate to Public Hearing - 35% to 30% - Public Hearing to PI/30% Design - 30% to 25%
Design & Permitting | Percentage of Construction Costs, including Contingency |  | Per HCEM 2026, Page A-2. Some judgement is necessary for small facilities where design may be a higher percentage such as 20%, or for larger facilities that might have normal design percentage plus NEPA and permitting. - Design/Engineering - 17.6%

## Shared Lane
Instructions:
| Planning Level Cost Estimates for Shared Lanes on Side of Roadway | [5 empty] | Enter quantities in colored cells. (Some cells may have additional information if you click on them.)
| Project Description | Units |  | Quantity |  |  | ** This estimate assumes no roadway widening, only pavement markings added to the existing asphalt surface.
| Length | Miles |  | 0 |  |  | Enter the length of the project in miles. Linear feet automatically populates.
| Are shared lanes on one or both sides? | Select ONE or BOTH |  | BOTH |  |  | Select ONE or BOTH sides of the roadway relative to location.
| Length | Linear Feet |  | 0 |  |  | Linear feet will auto populate.
| Intersections | Each |  | 0 |  |  | Enter the number of intersections in the project limits.
| Intersection Width (Average) | Linear Feet |  | 0 |  |  | Enter the average width of the intersection in the direction of travel.
| Pavement Markings |  |  | Quantity | Unit Cost | Total
| Shared Lanes Symbols | Each |  | 0 | 300 | 0 | Shared lane symbols are used every 250' and at intersections. This automatically populates.
| 5" White Retroreflective Pavement Marking | Linear Feet |  | 0 | 5 | 0 | LF automatically populated from Project Descriptions. Typically not needed for sharrow.
| 5" Yellow Retroreflective Pavement Marking | Linear Feet |  | 0 | 5 | 0 | Enter LF of new yellow pavement marking limits, if needed, and cost will auto populate. Typically, yellow striping not needed for lane next to parking
| Signs | Dimensions (not used) | Square Ft (not used) | Quantity | Each Unit Cost | Total
| Rd-17aP (Bike Lane Ahead) | 24" x 8" | 1.3 | 0 | 500 | 0 | Enter quantity of signs. Cost will auto populate based on quantity and unit cost
| Rd-17bP (Bike Lane Ends) | 24" x 8" | 1.3 | 0 | 500 | 0 | Enter quantity of signs. Cost will auto populate based on quantity and unit cost
| R4-4 (Right Turn Yield to Bikes) | 36" x 30" | 7.5 | 0 | 500 | 0 | Cost will auto populate based on number of intersections, quantity and unit cost
| R4-11 (Bikes May Use Full Lane) | 30" x 30" | 6.25 | 0 | 500 | 0 | Enter quantity of signs. Cost will auto populate based on quantity and unit cost
| Wayfinding Signing | varies | varies | 0 | 2000 | 0 | Enter quantity of signs. Cost will auto populate based on quantity and unit cost
| Subtotal |  |  |  |  | 0
| Maintenance of Traffic & Mobilization | Percentage of Subtotal |  |  | 25% | 0 | 25% assumes reasonable contingency for limited MOT. See Master List of Items.
| Construction Subtotal |  |  |  |  | 0
` | Contingency | Percentage of Construction Subtotal |  |  | 25% | 0 | 25% assumes minimal contingency for adding markings. See Master List of Items.
| Construction Total |  |  |  |  | 0
| Design & Permitting | Percentage of Construction Costs |  |  | 20% | 0 | 20% assumes reasonable contingency for design, likely no permitting. See Master List of Items.
| Total Project Costs for Design and Construction |  |  |  |  | 0

## Bike Lane Curbside
Instructions:
Planning Level Cost Estimates for Curb Side Bike Lane on Side of Roadway | [5 empty] | Enter quantities in colored cells. (Some cells may have additional information if you click on them.)
Project Description | Units |  | Quantity |  |  | ** This estimate assumes no roadway widening, only reallocating the existing pavement width. Must include some resurfacing where lane lines were ground off the asphalt surface.
Length | Miles |  | 0 |  |  | Enter the length of the project in miles. Linear feet automatically populates.
Are curb side bike lanes on one or both sides? | Select ONE or BOTH |  | BOTH |  |  | Select ONE or BOTH sides of the roadway relative to location.
Length | Linear Feet |  | 0 |  |  | Linear feet will auto populate.
Intersections | Each |  | 0 |  |  | Enter the number of intersections in the project limits.
Intersection Width (Avg) | Linear Feet |  | 0 |  |  | Enter the average width of the intersection in the direction of travel
Pavement Markings |  |  | Quantity | Unit Cost | Total
Bike Lane Symbols | Each |  | 0 | 300 | 0 | Shared lane symbols are used every 1/4 mile and at intersections. This automatically populates. [MD Bicycle Policy & Design Guidelines, Section 2.2]
5" White Retroreflective Pavement Marking | Linear Feet |  | 0 | 5 | 0 | LF automatically populated from Project Descriptions for 2 parallel white lines
5" Yellow Retroreflective Pavement Marking | Linear Feet |  | 5 | 5 | 25 | Enter LF of new yellow pavement marking limits, if needed, and cost will auto populate. Typically, yellow striping not needed for lane next to parking
Green Pavement Marking | Square Foot |  | 0 | 20 | 0 | SF automatically populated from Project Description for 6' wide green markings across intersection width (plus 10' further on each side)
Pavement Resurfacing |  | Length (feet) | Width (feet) | Unit Cost | Total
Fine/Micro Milling Existing Pavement Markings Only (no resurfacing) | Square Yard | 0 | 0 | 6 | 0 | Enter length and width in FEET of milling/grinding area for JUST THE PAVEMENT MARKINGS. Cost is calculated per square yard and conversion will automatically occur in total.
Milling of Hot Mix Asphalt Surface (up to 1") | Square Yard | 0 | 0 | 5 | 0 | Enter length and width in FEET of milling/grinding area. Cost is calculated per square yard and conversion will automatically occur in total.
Resurface 1" Hot Mix Asphalt for Roadway | Ton | 0 | 0 | 130 | 0 | Enter length and width in FEET of resurfacing area (generally the same as the Milling area). Cost is calculated per ton and conversion will automatically occur in total.
Signs | Dimensions (not used) | Square Ft (not used) | Quantity | Unit Cost | Total
R3-17 (Bike Lane) | 24" x 18" | 3 | 0 | 500 | 0 | Cost will auto populate based on length and number of intersections, quantity, SF, and unit cost
Rd-17aP (Bike Lane Ahead) | 24" x 8" | 1.3 | 0 | 500 | 0 | Enter quantity of signs. Cost will auto populate based on quantity and unit cost
Rd-17bP (Bike Lane Ends) | 24" x 8" | 1.3 | 0 | 500 | 0 | Enter quantity of signs. Cost will auto populate based on quantity and unit cost
R4-4 (Right Turn Yield to Bikes) | 36" x 30" | 7.5 | 0 | 500 | 0 | Cost will auto populate based on number of intersections, quantity and unit cost
R4-11 (Bikes May Use Full Lane) | 30" x 30" | 6.25 | 0 | 500 | 0 | Enter quantity of signs. Cost will auto populate based on quantity and unit cost
Subtotal |  |  |  |  | 25
Maintenance of Traffic & Mobilization | Percentage of Subtotal |  |  | 40% | 10 | 40% assumes reasonable contingency for MOT to stripe existing roadway. See Master List of Items.
Construction Subtotal |  |  |  |  | 35
Contingency | Percentage of Construction Subtotal |  |  | 25% | 8.75 | 25% assumes minimal contingency for repurposing roadway pavement area. See Master List of Items.
Construction Total |  |  |  |  | 43.75
Design & Permitting | Percentage of Construction Costs |  |  | 20% | 8.75 | 20% assumes reasonable contingency for design, likely no permitting. See Master List of Items.
Total Project Costs for Design and Construction |  |  |  |  | 100

## Bike Lane w Parking
Instructions:
Planning Level Cost Estimates for Bike Lane Against Parking Lane on Side of Roadway | [5 empty] | Enter quantities in colored cells. (Some cells may have additional information if you click on them.)
Project Description | Units |  | Quantity |  |  | ** This estimate assumes no roadway widening, only reallocating the existing pavement width. Must include some resurfacing where lane lines were ground off the asphalt surface.
Length | Miles |  | 0 |  |  | Enter the length of the project in miles. Linear feet automatically populates.
Are curb side bike lanes on one or both sides? | Select ONE or BOTH |  | BOTH |  |  | Select ONE or BOTH sides of the roadway relative to location
Length | Linear Feet |  | 0 |  |  | Linear feet will auto populate.
Intersections | Each |  | 0 |  |  | Enter the number of intersections in the project limits.
Intersection Width (Avg) | Linear Feet |  | 0 |  |  | Enter the average width of the intersection in the direction of travel
Pavement Markings |  |  | Quantity | Unit Cost | Total
Bike Lane symbols | Each |  | 0 | 300 | 0 | Shared lane symbols are used every 1/4 mile and at intersections. This automatically populates. [MD Bicycle Policy & Design Guidelines, Section 2.2]
5" White Retroreflective Pavement Marking | Linear Feet |  | 0 | 5 | 0 | LF automatically populated from Project Descriptions for 2 parallel white lines
5" Yellow Retroreflective Pavement Marking | Linear Feet |  | 0 | 5 | 0 | Enter LF of new yellow pavement marking limits, if needed, and cost will auto populate. Typically, yellow striping not needed for lane next to parking
Green Pavement Marking | Square Foot |  | 0 | 20 | 0 | SF automatically populated from Project Description for 6' wide green markings across intersection width (plus 10' further on each side)
Pavement Resurfacing |  | Length (feet) | Width (feet) | Unit Cost | Total
Fine/Micro Milling Existing Pavement Markings Only (no resurfacing) | Square Yard | 0 | 0 | 6 | 0 | Enter length and width in FEET of milling/grinding area for JUST THE PAVEMENT MARKINGS. Cost is calculated per square yard and conversion will automatically occur in total.
Milling of Hot Mix Asphalt Surface (up to 1") | Square Yard | 0 | 0 | 5 | 0 | Enter length and width in FEET of milling/grinding area. Cost is calculated per square yard and conversion will automatically occur in total.
Resurface 1" Hot Mix Asphalt for Roadway | Ton | 0 | 0 | 130 | 0 | Enter length and width in FEET of resurfacing area (generally the same as the Milling area). Cost is calculated per ton and conversion will automatically occur in total.
Signs | Dimensions (not used) | Square Ft (not used) | Quantity | Unit Cost | Total
R3-17 (Bike Lane) | 24" x 18" | 3 | 0 | 500 | 0 | Cost will auto populate based on length and number of intersections, quantity, SF, and unit cost
Rd-17aP (Bike Lane Ahead) | 24" x 8" | 1.3 | 0 | 500 | 0 | Enter quantity of signs. Cost will auto populate based on quantity and unit cost
Rd-17bP (Bike Lane Ends) | 24" x 8" | 1.3 | 0 | 500 | 0 | Enter quantity of signs. Cost will auto populate based on quantity and unit cost
R4-4 (Right Turn Yield to Bikes) | 36" x 30" | 7.5 | 0 | 500 | 0 | Cost will auto populate based on number of intersections, quantity and unit cost
R4-11 (Bikes May Use Full Lane) | 30" x 30" | 6.25 | 0 | 500 | 0 | Enter quantity of signs. Cost will auto populate based on quantity and unit cost
Subtotal |  |  |  |  | 0
Maintenance of Traffic & Mobilization | Percentage of Subtotal |  |  | 40% | 0 | 40% assumes reasonable contingency for MOT to stripe existing roadway. See Master List of Items.
Construction Subtotal |  |  |  |  | 0
Contingency | Percentage of Construction Subtotal |  |  | 25% | 0 | 25% assumes minimal contingency for repurposing roadway pavement area. See Master List of Items.
Construction Total |  |  |  |  | 0
Design & Permitting | Percentage of Construction Costs |  |  | 20% | 0 | 20% assumes reasonable contingency for design, likely no permitting. See Master List of Items.
Total Project Costs for Design and Construction |  |  |  |  | 0

## Buffer Bike Lane Curbside
Instructions:
Planning Level Cost Estimates for Curb Side Buffered Bike Lane on Side of Roadway | [5 empty] | Enter quantities in colored cells. (Some cells may have additional information if you click on them.)
Project Description | Units |  | Quantity |  |  | ** This estimate assumes no roadway widening, only reallocating the existing pavement width. Typically, it includes converting a travel lane to a bike lane or other similar pavement repurposing. May include some resurfacing where lane lines would be ground off to reallocate width.
Length | Miles |  | 0 |  |  | Enter the length of the project in miles. Linear feet automatically populates.
Are curb side bike lanes on one or both sides? | Select ONE or BOTH |  | BOTH |  |  | Select ONE or BOTH sides of the roadway relative to location.
Length | Linear Feet |  | 0 |  |  | Linear feet will auto populate.
Intersections | Each |  | 0 |  |  | Enter the number of intersections in the project limits.
Intersection Width (Avg) | Linear Feet |  | 0 |  |  | Enter the average width of the intersection in the direction of travel
Pavement Markings |  |  | Quantity | Unit Cost | Total
Bike Lane Symbols | Each |  | 0 | 300 | 0 | Shared lane symbols are used every 1/4 mile and at intersections. This automatically populates. [MD Bicycle Policy & Design Guidelines, Section 2.2]
5" White Retroreflective Pavement Marking | Linear Feet |  | 0 | 5 | 0 | LF automatically populated from Project Descriptions for 2 parallel white lines.
5" White Retroreflective Pavement Marking for 3' Buffer, 10' Spacing | Linear Feet |  | 0 | 1.25 | 0 | Enter LF of new dashed pavement marking limits, if needed, and cost will auto populate.
5" Yellow Retroreflective Pavement Marking | Linear Feet |  | 0 | 5 | 0 | Enter LF of new yellow pavement marking limits, if needed, and cost will auto populate.
Green Pavement Marking | Square Foot |  | 0 | 20 | 0 | SF automatically populated from Project Description for 6' wide green markings across intersection width (plus 10' further on each side)
Pavement Resurfacing |  | Length (feet) | Width (feet) | Unit Cost | Total
Fine/Micro Milling Existing Pavement Markings Only (no resurfacing) | Square Yard | 0 | 0 | 6 | 0 | Enter length and width in FEET of milling/grinding area for JUST THE PAVEMENT MARKINGS. Cost is calculated per square yard and conversion will automatically occur in total.
Milling of Hot Mix Asphalt Surface (up to 1") | Square Yard | 0 | 0 | 5 | 0 | Enter length and width in FEET of milling/grinding area. Cost is calculated per square yard and conversion will automatically occur in total.
Resurface 1" Hot Mix Asphalt for Roadway | Ton | 0 | 0 | 130 | 0 | Enter length and width in FEET of resurfacing area (generally the same as the Milling area). Cost is calculated per ton and conversion will automatically occur in total.
Signs | Dimensions (not used) | Square Ft (not used) | Quantity | Unit Cost | Total
R3-17 (Bike Lane) | 24" x 18" | 3 | 0 | 500 | 0 | Cost will auto populate based on length and number of intersections, quantity, SF, and unit cost
Rd-17aP (Bike Lane Ahead) | 24" x 8" | 1.3 | 0 | 500 | 0 | Enter quantity of signs. Cost will auto populate based on quantity and unit cost
Rd-17bP (Bike Lane Ends) | 24" x 8" | 1.3 | 0 | 500 | 0 | Enter quantity of signs. Cost will auto populate based on quantity and unit cost
R4-4 (Right Turn Yield to Bikes) | 36" x 30" | 7.5 | 0 | 500 | 0 | Cost will auto populate based on number of intersections, quantity and unit cost
R4-11 (Bikes May Use Full Lane) | 30" x 30" | 6.25 | 0 | 500 | 0 | Enter quantity of signs. Cost will auto populate based on quantity and unit cost
Intersections |  |  | Quantity | Unit Cost | Total
New Bicycle Signal Heads on Existing Signal Poles (incl. heads, wiring, conduit, new or upgraded controller) | Per Crossing |  | 0 | 20000 | 0 | Enter number of intersection crossings that require new bicycle signal heads on existing poles, reconstruction, or partial new signal heads.
New Small Traffic Signals for Designated Bicycle Lane or Separate Facility (incl. heads, poles, push-buttons, wiring, conduit, new or upgraded controller) | Per Crossing |  | 0 | 30000 | 0 | Enter number of intersection crossings that require separate small bicycle signals, assuming on own poles.
Separation | Length (feet) |  | Quantity | Unit Cost | Total
Flex Posts (each, 10' spacing) | 0 |  | 0 | 225 | 0 | Enter project length in LF where flex posts will be located. Quantity and cost will auto populate.
Low profile, pre-fab concrete barrier (10' length). Either continuous or spaced 10' apart | 0 | (assume space between is not included in length) |  | 400 | 0 | Enter project length in LF where concrete barrier will be located. If barriers are spaced 10' apart, divide total length in half. Cost will auto populate.
Concrete Planters (each, 6' length, 25' spacing) | 0 |  | 0 | 2300 | 0 | Enter project length in LF where planter will be located. Quantity and cost will auto populate.
Raised Concrete Median (LF, assume 4' wide) | 0 |  |  | 250 | 0 | Enter length (LF) where concrete median will be located. Cost will auto populate.
Shared Bus Boarding Areas/Islands - Concrete Island | 0 |  |  | 250 | 3300 | Enter length (LF) of shared bus boarding area/island plus tapers and adjacent ramps. Cost is per LF plus $3300 for signs, detectible warning surface - will auto populate.
Shared Bus Boarding Areas/Islands - Modular Island |  |  | 0 | 37000 | 0 | Enter number of modular bus boarding areas. Assumed size is 6'wide x 40'long, plus 6'x6' connector with 2 ramps, plus connections to sidewalk.
Subtotal |  |  |  |  | 3300
Maintenance of Traffic & Mobilization | Percentage of Subtotal |  |  | 50% | 1650 | 50% assumes reasonable contingency for MOT within existing roadway. See Master List of Items.
Construction Subtotal |  |  |  |  | 4950
Contingency | Percentage of Construction Subtotal |  |  | 30% | 1485 | 30% assumes contingency for separated roadway pavement area. See Master List of Items.
Construction Total |  |  |  |  | 6435
Design & Permitting | Percentage of Construction Costs |  |  | 20% | 1287 | 20% assumes reasonable contingency for design, likely no permitting. See Master List of Items.
Total Project Costs for Design and Construction |  |  |  |  | 7700

## Protected Two-Way Bike Lane
Instructions:
Planning Level Cost Estimates for Curb Side Protected Two-Way Bike Lane | [5 empty] | Enter quantities in colored cells. (Some cells may have additional information if you click on them.)
Project Description |  |  | Quantity |  |  | ** This estimate assumes no roadway widening, only reallocating the existing pavement width. Typically, it includes converting a travel lane to a bike lane or other similar pavement repurposing. May include some resurfacing where lane lines would be ground off to reallocate width.
Length | Miles |  | 0 |  |  | Enter the length of the project in miles. Linear feet automatically populates.
Are curb side bike lanes on one or both sides? | Select ONE or BOTH |  | BOTH |  |  | Select ONE or BOTH sides of the roadway relative to location.
Length | Linear Feet |  | 0 |  |  | Linear feet will auto populate.
Intersections | Each |  | 0 |  |  | Enter the number of intersections in the project limits.
Intersection Width (Avg) | Linear Feet |  | 0 |  |  | Enter the average width of the intersection in the direction of travel.
Pavement Markings |  |  | Quantity | Unit Cost | Total
Bike Lane symbols | Each |  | 0 | 300 | 0 | Shared lane symbols are used every 1/4 mile and at intersections. This automatically populates. [MD Bicycle Policy & Design Guidelines, Section 2.2]
5" White Retroreflective Pavement Marking | Linear Feet |  | 0 | 5 | 0 | LF automatically populated from Project Descriptions for 2 parallel white lines.
5" White Retroreflective Pavement Marking for 3' Buffer, 10' Spacing | Linear Feet |  | 0 | 1.25 | 0 | Enter LF of new dashed pavement marking limits, if needed, and cost will auto populate.
5" Yellow Retroreflective Pavement Marking | Linear Feet |  | 0 | 5 | 0 | Enter LF of new yellow pavement marking limits, if needed, and cost will auto populate.
Green Pavement Marking | Square Foot |  | 0 | 20 | 0 | SF automatically populated from Project Description for 6' wide green markings across intersection width (plus 10' further on each side)
Pavement Resurfacing |  | Length (feet) | Width (feet) | Unit Cost | Total
Fine/Micro Milling Existing Pavement Markings Only (no resurfacing) | Square Yard | 0 | 0 | 6 | 0 | Enter length and width in FEET of milling/grinding area for JUST THE PAVEMENT MARKINGS. Cost is calculated per square yard and conversion will automatically occur in total.
Milling of Hot Mix Asphalt Surface (up to 1") | Square Yard | 0 | 0 | 5 | 0 | Enter length and width in FEET of milling/grinding area. Cost is calculated per square yard and conversion will automatically occur in total.
Resurface 1" Hot Mix Asphalt for Roadway | Ton | 0 | 0 | 130 | 0 | Enter length and width in FEET of resurfacing area (generally the same as the Milling area). Cost is calculated per ton and conversion will automatically occur in total.
Signs | Dimensions (not used) | Square Ft (not used) | Quantity | Unit Cost (Each) | Total
R3-17 (Bike Lane) | 24" x 18" | 3 | 0 | 500 | 0 | Cost will auto populate based on length and number of intersections, quantity, SF, and unit cost
Rd-17aP (Bike Lane Ahead) | 24" x 8" | 1.3 | 0 | 500 | 0 | Enter quantity of signs. Cost will auto populate based on quantity and unit cost
Rd-17bP (Bike Lane Ends) | 24" x 8" | 1.3 | 0 | 500 | 0 | Enter quantity of signs. Cost will auto populate based on quantity and unit cost
R4-4 (Right Turn Yield to Bikes) | 36" x 30" | 7.5 | 0 | 500 | 0 | Cost will auto populate based on number of intersections, quantity and unit cost
R4-11 (Bikes May Use Full Lane) | 30" x 30" | 6.25 | 0 | 500 | 0 | Enter quantity of signs. Cost will auto populate based on quantity and unit cost
Separation | Length (feet) |  | Quantity | Unit Cost | Total
Flex Posts (each, 10' spacing) | 0 |  | 0 | 225 | 0 | Enter project length in LF where flex posts will be located. Quantity and cost will auto populate.
Low profile, pre-fab concrete barrier (10' length). Either continuous or spaced 10' apart | 0 | (assume space between is not included in length) |  | 400 | 0 | Enter project length in LF where concrete barrier will be located. If barriers are spaced 10' apart, divide total length in half. Cost will auto populate.
Concrete Planters (each, 6' length, 25' spacing) | 0 |  | 0 | 2300 | 0 | Enter project length in LF where planter will be located. Quantity and cost will auto populate.
Raised Concrete Median (LF, assume 4' wide) | 0 |  |  | 250 | 0 | Enter length (LF) where concrete median will be located. Cost will auto populate.
Intersections |  |  | Quantity | Unit Cost | Total
New Bicycle Signal Heads on Existing Signal Poles (incl. heads, wiring, conduit, new or upgraded controller) | Per Crossing |  | 0 | 20000 | 0 | Enter number of intersection crossings that require new bicycle signal heads on existing poles, reconstruction, or partial new signal heads.
New Small Traffic Signals for Designated Bicycle Lane or Separate Facility (incl. heads, poles, push-buttons, wiring, conduit, new or upgraded controller) | Per Crossing |  | 0 | 30000 | 0 | Enter number of intersection crossings that require separate small bicycle signals, assuming on own poles.
Traffic Calming and Additional Features |  |  | Quantity | Unit Cost | Total
Curb Extensions | Each |  | 0 | 22000 | 0
Landscaped Chicanes | Each |  | 0 | 30000 | 0 | Enter the quantity. Cost will auto populate.
Raised Crosswalk | Each |  | 0 | 13000 | 0 | Enter the quantity. Cost will auto populate.
Bicycle-friendly storm grates | Each |  | 0 | 1000 | 0 | Enter the quantity. Cost will auto populate.
Shared Bus Boarding Areas/Islands - Concrete Island | Linear Feet |  | 0 | 250 | 3300 | Enter length (LF) of shared bus boarding area/island plus tapers and adjacent ramps. Cost is per LF plus $3300 for signs, detectible warning surface - will auto populate.
Shared Bus Boarding Areas/Islands - Modular Island | Each |  | 0 | 37000 | 0 | Enter number of modular bus boarding areas. Assumed size is 6'wide x 40'long, plus 6'x6' connector with 2 ramps, plus connections to sidewalk.
Subtotal |  |  |  |  | 3300
Maintenance of Traffic & Mobilization | Percentage of Subtotal |  |  | 50% | 1650 | 50% assumes reasonable contingency for MOT within existing roadway. See Master List of Items.
Construction Subtotal |  |  |  |  | 4950
Contingency | Percentage of Construction Subtotal |  |  | 30% | 1485 | 30% assumes contingency for separated roadway pavement area. See Master List of Items.
Construction Total |  |  |  |  | 6435
Design & Permitting | Percentage of Construction Costs |  |  | 20% | 1287 | 20% assumes reasonable contingency for design and permitting. See Master List of Items.
Total Project Costs for Design and Construction |  |  |  |  | 7700

## Bike Blvd
Instructions:
Planning Level Cost Estimates for Bicycle Boulevard/Neighborhood Greenway Corridor Improvements | [5 empty] | Enter quantities in colored cells. (Some cells may have additional information if you click on them.)
Project Descriptions |  |  | Quantity
Length | Miles |  | 0 |  |  | Enter the length of the project in miles. Linear feet automatically populates.
Length | Linear Feet |  | 0 |  |  | Linear feet will auto populate.
Does project include bike boulevard in same direction as traffic flow? | Select YES or NO |  | YES |  |  | Select YES or NO regarding direction of bicycle travel.
Intersections | Each |  | 0 |  |  | Enter the number of intersections in the project limits.
Intersection Width (Avg) | Linear Feet |  | 0 |  |  | Enter the average width of the intersection in the direction of travel.
Are contraflow lanes part of the project? | Select ONE or BOTH |  | YES |  |  | See example photo for contraflow bike lane à
Contraflow Length | Linear Feet |  | 0 |  |  | Enter length of contraflow lane.
Contraflow Intersections | Each |  | 0 |  |  | Enter number of intersections that contraflow lane crosses.
Pavement Markings |  |  | Quantity | Unit Cost | Total
Shared Lanes symbols | Each |  | 0 | 300 | 0 | Shared lane symbols are used every 1/4 mile and at intersections. This automatically populates. [MD Bicycle Policy & Design Guidelines, Section 2.2].
5" White Retroreflective Pavement Marking | Linear Feet |  | 0 | 5 | 0 | LF automatically populated from Project Descriptions for 2 parallel white lines.
5" Yellow Retroreflective Pavement Marking | Linear Feet |  | 0 | 1.25 | 0 | LF automatically populated from Project Descriptions for contraflow lanes - includes double yellow stripe.
Green Pavement Marking | Square Foot |  | 0 | 5 | 0 | SF automatically populated from Project Description for 6' wide green markings across intersection width (plus 10' further on each side).
Signs | Dimensions (not used) | Square Ft (not used) | Quantity | Unit Cost | Total
Rd-17aP (Bike Lane Ahead) | 24" x 8" | 1.3 | 0 | 500 | 0 | Enter quantity of signs. Cost will auto populate based on quantity and unit cost.
Rd-17bP (Bike Lane Ends) | 24" x 8" | 1.3 | 0 | 500 | 0 | Enter quantity of signs. Cost will auto populate based on quantity and unit cost.
R4-4 (Right Turn Yield to Bikes) | 36" x 30" | 7.5 | 0 | 500 | 0 | Cost will auto populate based on number of intersections, quantity and unit cost.
R4-11 (Bikes May Use Full Lane) | 30" x 30" | 6.25 | 0 | 500 | 0 | Enter quantity of signs. Cost will auto populate based on quantity and unit cost.
D11-1 (Bike Route) | 24" x 8" | 1.3 | 0 | 500 | 0 | Enter quantity of signs. Cost will auto populate based on quantity and unit cost.
Intersections |  |  | Quantity | Unit Cost | Total
New Bicycle Signal Heads on Existing Signal Poles (incl. heads, wiring, conduit, new or upgraded controller) | Per Crossing |  | 0 | 20000 | 0 | Enter number of intersection crossings that require new bicycle signal heads on existing poles, reconstruction, or partial new signal heads.
New Small Traffic Signals for Designated Bicycle Lane or Separate Facility (incl. heads, poles, push-buttons, wiring, conduit, new or upgraded controller) | Per Crossing |  | 0 | 30000 | 0 | Enter number of intersection crossings that require separate small bicycle signals, assuming on own poles.
Traffic Calming Features |  | Length (feet) | Quantity | Unit Cost | Total
Flex posts (10' spacing) for additional use | Each | 0 | 0 | 225 | 0 | Enter length of project where flex posts will be included.
Flex posts (miscellaneous placement) | Each |  | 0 | 225 | 0 | See example in photo for misc. placement of flex posts à
Bicycle-friendly speed humps | Each |  | 0 | 5000 | 0 | Enter quantity and cost will auto populate.
Curb Extensions | Per Intersection |  | 0 | 22000 | 0 | Enter number of intersections and cost will auto populate.
Landscaped Chicanes | Each |  | 0 | 30000 | 0 | Enter quantity and cost will auto populate.
Raised Crosswalk | Each |  | 0 | 13000 | 0 | Enter quantity and cost will auto populate.
Raised Intersection | Each |  | 0 | 100000 | 0 | Enter quantity and cost will auto populate.
Mini-Roundabout | Per Intersection |  | 0 | 0 | 0 | This has a wide range of potential costs from $80,000 to $250,000. Local jurisdiction should choose a cost based on how complicated a new mini-roundabout would be. Low end is mini-roundabout on simple neighborhood street. High end is larger roundabout or has more potential conflicts, but still falls predominently within the existing right-of-way.
Bicycle-friendly storm grates | Each |  | 0 | 1000 | 0 | Enter quantity and cost will auto populate.
Subtotal |  |  |  |  | 0
Maintenance of Traffic & Mobilization | Percentage of Subtotal |  |  | 40% | 0 | 40% assumes reasonable contingency for MOT to stripe existing roadway. See Master List of Items.
Construction Subtotal |  |  |  |  | 0
Contingency | Percentage of Construction Subtotal |  |  | 30% | 0 | 30% assumes contingency for separated roadway pavement area and traffic calming. See Master List of Items.
Construction Total |  |  |  |  | 0
Design & Permitting | Percentage of Construction Costs |  |  | 20% | 0 | 20% assumes reasonable contingency for design and permitting. See Master List of Items.
Total Project Costs for Design and Construction |  |  |  |  | 0

## Shared-Use Paths
Instructions:
Planning Level Cost Estimates for Shared-use Path | [5 empty] | Enter quantities in colored cells. (Some cells may have additional information if you click on them.)
Facility Type |  | Length (miles) | Unit Cost (per mile) | Total
Shared-use Path |  | 0 | 1800000 | 0 |  | Enter the length in miles of the shared-use path.
Questions regarding the environment that affect the unit cost:
Will path have LOW or HIGH environmental impacts? |  | HIGH |  |  | 0 | Select LOW or HIGH for environmental impacts. Cost will be increased by 20% if HIGH impacts.
Will the path have pervious or permeable pavement? |  | YES |  |  | 0 | Select YES or NO for pervious pavement. Pervious pavement is more expensive than regular pavement. Cost will be increased by 50% if YES.
Will path have LOW or HIGH barriers, constraints, or other impacts? |  | HIGH |  |  | 0 | Select LOW or HIGH for surrounding constraints. Cost will be increased by 30% if HIGH.
Subtotal of path, taking into consideration surrounding environment = |  |  |  |  | 0
Retaining Walls |  | Length (feet) | Height (feet) | Unit Cost (SF) | Total
| Wall 1 | 0 | 6 | 295 | 0 | Assume retaining walls are 6-feet tall. Enter length and cost will auto populate.
| Wall 2 | 0 | 6 | 295 | 0 | Assume retaining walls are 6-feet tall. Enter length and cost will auto populate.
| Wall 3 | 0 | 6 | 295 | 0 | Assume retaining walls are 6-feet tall. Enter length and cost will auto populate.
Bridges |  | Length (feet) | Width (feet) | Unit Cost (SF) | Total
| Bridge 1 | 0 | 17 | 472.5 | 0 | Enter length. Width calculated assuming trail is 12' wide plus 1-foot offset to barrier plus and 1.5 feet for width of parapet (x2 for both sides)
| Bridge 2 | 0 | 17 | 472.5 | 0 | Enter length. Width calculated assuming trail is 12' wide plus 1-foot offset to barrier plus and 1.5 feet for width of parapet (x2 for both sides)
| Pre-fabricated Bridge 1 | 0 | 17 | 250 | 0 | Enter length. Width calculated assuming trail is 12' wide plus 1-foot offset to barrier plus and 1.5 feet for width of parapet (x2 for both sides)
| Pre-fabricated Bridge 2 | 0 | 17 | 250 | 0 | Enter length. Width calculated assuming trail is 12' wide plus 1-foot offset to barrier plus and 1.5 feet for width of parapet (x2 for both sides)
Boardwalk |  | Length (feet) | Width (feet) | Unit Cost | Total
Boardwalk (with railings) |  | 0 | 10 | 125 | 0 | Enter length. Width calculated by assuming trail is 12' wide plus 0.5 foot for width of parapet (x2 for both sides). Say 13 feet wide.
Boardwalk (with railings) |  | 0 | 10 | 125 | 0 | Enter length. Width calculated by assuming trail is 12' wide plus 0.5 foot for width of parapet (x2 for both sides). Say 13 feet wide.
Boardwalk (without railings, close to ground) |  | 0 | 10 | 90 | 0 | Enter length. Width calculated by assuming trail is 12' wide plus 0.5 foot for width of parapet (x2 for both sides). Say 13 feet wide.
Boardwalk (without railings, close to ground) |  | 0 | 10 | 90 | 0 | Enter length. Width calculated by assuming trail is 12' wide plus 0.5 foot for width of parapet (x2 for both sides). Say 13 feet wide.
Tunnels |  | Length (feet) | Width (feet) | Unit Cost (SF) | Total
| Tunnel 1 | 0 | 16 | 2500 | 0 | Assume tunnel is 14' wide plus 1-foot for width of walls (x2 for both sides).
| Tunnel 2 | 0 | 16 | 2500 | 0 | Assume tunnel is 14' wide plus 1-foot for width of walls (x2 for both sides).
Intersections |  |  | Quantity | Unit Cost | Total
New Bicycle Signal Heads on Existing Signal Poles (incl. heads, wiring, conduit, new or upgraded controller) | Per Crossing |  | 0 | 20000 | 0 | Enter number of intersection crossings that require new bicycle signal heads on existing poles, reconstruction, or partial new signal heads.
New Small Traffic Signals for Designated Bicycle Lane or Separate Facility (incl. heads, poles, push-buttons, wiring, conduit, new or upgraded controller) | Per Crossing |  | 0 | 30000 | 0 | Enter number of intersection crossings that require separate small bicycle signals, assuming on own poles.
Lighting |  | Length (feet) | # of Poles (both sides) | Unit Cost (Per Pole) | Total
| Segment 1 | 0 | 0 | 11000 | 0 | Assume poles are spaced 75 feet apart and are on both sides of shared use path (# poles doubled). Enter length of path where lighting proposed, then # poles and cost auto populate.
| Segment 2 | 0 | 0 | 11000 | 0 | Assume poles are spaced 75 feet apart and are on both sides of shared use path (# poles doubled). Enter length of path where lighting proposed, then # poles and cost auto populate.
| Segment 3 | 0 | 0 | 11000 | 0 | Assume poles are spaced 75 feet apart and are on both sides of shared use path (# poles doubled). Enter length of path where lighting proposed, then # poles and cost auto populate.
Railroad Protection Services |  | Quantity |  | Unit Cost (per Location) | Total
Fencing (6-feet tall) between RR and Path | Linear Feet | 0 |  | 45 | 0 | Enter length where fencing is proposed.
RR Crossing Monitoring during Construction | Each Crossing | 0 |  | 750000 | 0 | Enter number of locations where path crosses railroad.
Subtotal |  |  |  |  | 0
Maintenance of Traffic & Mobilization | Percentage of Subtotal |  |  | 40% | 0 | 40% assumes reasonable contingency for construction resources generally off existing roadway. See Master List of Items.
Construction Subtotal |  |  |  |  | 0
Contingency | Percentage of Construction Subtotal |  |  | 35% | 0 | Contingency would likely be on high end when doing full new construction of path. See Master List of Items.
Construction Total |  |  |  |  | 0
Design & Permitting | Percentage of Construction Costs |  |  | 20% | 0 | 20% assumes reasonable contingency for design and permitting. See Master List of Items.
Total Project Costs for Design and Construction |  |  |  |  | 0

## Complete Sts Intersection
Instructions:
Planning Level Cost Estimates for Complete Streets Intersection | [5 empty] | Enter quantities in colored cells. (Some cells may have additional information if you click on them.)
Project Descriptions |  |  | Quantity
Length | Miles |  | 0 |  |  | Enter the length of the project in miles. Linear feet automatically populates.
Length | Linear Feet |  | 0 |  |  | Linear feet will auto populate.
Intersections | Each |  | 0 |  |  | Enter the number of intersections in the project limits.
Intersection Width (Avg) | Linear Feet |  | 0 |  |  | Enter the average width of the intersection in the direction of travel.
Pavement Markings |  |  | Quantity | Unit Cost | Total
Bike Lane symbols | Each |  | 0 | 300 | 0 | Shared lane symbols are used every 1/4 mile and at intersections. This automatically populates. [MD Bicycle Policy & Design Guidelines, Section 2.2].
5" White Retroreflective Pavement Marking | Linear Feet |  | 0 | 5 | 0 | LF automatically populated from Project Descriptions for 2 parallel white lines.
5" White Retroreflective Pavement Marking for 3' Buffer, 10' Spacing | Linear Feet |  | 0 | 1.25 | 0 | Enter linear feet where dashed lane line markings are needed. There is low likelihood of this item in an intersection.
5" Yellow Retroreflective Pavement Marking | Linear Feet |  | 0 | 5 | 0 | Enter LF of new yellow pavement marking limits, if needed, and cost will auto populate.
Green Pavement Marking | Square Foot |  | 0 | 20 | 0 | SF automatically populated from Project Description for 6' wide green markings across intersection width (plus 10' further on each side).
Signs | Dimensions (not used) | Square Ft (not used) | Quantity | Unit Cost | Total
Rd-17aP (Bike Lane Ahead) | 24" x 8" | 1.3 | 0 | 500 | 0 | Enter quantity of signs. Cost will auto populate based on quantity and unit cost.
Rd-17bP (Bike Lane Ends) | 24" x 8" | 1.3 | 0 | 500 | 0 | Enter quantity of signs. Cost will auto populate based on quantity and unit cost.
R4-4 (Right Turn Yield to Bikes) | 36" x 30" | 7.5 | 0 | 500 | 0 | Cost will auto populate based on number of intersections, assuming 4 signs per intersection.
R4-11 (Bikes May Use Full Lane) | 30" x 30" | 6.25 | 0 | 500 | 0 | Enter quantity of signs. Cost will auto populate based on quantity and unit cost.
Separation | Length (feet) |  | Quantity | Unit Cost | Total
Flex Posts (each, 10' spacing) | 0 |  | 0 | 225 | 0 | Enter project length in LF where flex posts will be located. Quantity and cost will auto populate.
Low profile, pre-fab concrete barrier (10' length). Either continuous or spaced 10' apart | 0 | (assume space between is not included in length) |  | 400 | 0 | Enter project length in LF where concrete barrier will be located. If barriers are spaced 10' apart, divide total length in half. Cost will auto populate.
Concrete Planters (each, 6' length, 25' spacing) | 0 |  | 0 | 2300 | 0 | Enter project length in LF where planter will be located. Quantity and cost will auto populate.
Intersections |  |  | Quantity | Unit Cost | Total
New Bicycle Signal Heads on Existing Signal Poles (incl. heads, wiring, conduit, new or upgraded controller) | Per Crossing |  | 0 | 20000 | 0 | Enter number of intersection crossings that require new bicycle signal heads, reconstruction, or partial new signal heads.
New Small Traffic Signals for Designated Bicycle Lane or Separate Facility (incl. heads, poles, push-buttons, wiring, conduit, new or upgraded controller) | Per Crossing |  | 0 | 30000 | 0 | Enter number of intersection crossings that require separate small bicycle signals, assuming on own poles.
New Pedestrian Signal Heads on Existing Signal Poles (incl. heads, push-buttons, accessible ped signals, wiring, conduit, new/upgraded controller) | Per Crossing |  | 0 | 20000 | 0 | Enter number of intersection crossings that require pedestrian signal heads on existing poles, but not full reconstruction or signal pole impacts.
Traffic Calming Features |  |  | Quantity | Unit Cost | Total
Curb Extensions | Per Intersection |  | 0 | 22000 | 0 | Enter number of intersections and cost will auto populate.
Landscaped Chicanes | Each |  | 0 | 30000 | 0 | Enter quantity and cost will auto populate.
Raised Crosswalk | Each |  | 0 | 13000 | 0 | Enter quantity and cost will auto populate.
Raised Intersection | Each |  | 0 | 100000 | 0 | Enter quantity and cost will auto populate.
Mini-Roundabout | Per Intersection |  | 0 | 0 | 0 | Enter number of intersections. Enter unit cost in range of $60,000 to $250,000. Total cost will auto populate. Choose cost based on how complicated new mini-roundabout would be. Low end is mini-roundabout on simple neighborhood street. High end is larger or has more potential conflicts, but still falls predominently within the existing right-of-way.
Pedestrian Refuge Island | Each |  | 0 | 7000 | 0 | Enter quantity and cost will auto populate.
Bicycle-friendly speed humps | Each |  | 0 | 5000 | 0 | Enter quantity and cost will auto populate.
Bicycle-friendly storm grates | Each |  | 0 | 1000 | 0 | Enter quantity and cost will auto populate.
Shared Bus Boarding Areas/Islands - Concrete Island | Linear Feet |  | 0 | 250 | 3300 | Enter length (LF) of shared bus boarding area/island plus tapers and adjacent ramps. Cost is per LF plus $3300 for signs, detectible warning surface - will auto populate.
Shared Bus Boarding Areas/Islands - Modular Island | Each |  | 0 | 37000 | 0 | Enter number of modular bus boarding areas. Assumed size is 6'wide x 40'long, plus 6'x6' connector with 2 ramps, plus connections to sidewalk.
Subtotal |  |  |  |  | 3300
Maintenance of Traffic & Mobilization | Percentage of Subtotal |  |  | 65% | 2145 | 65% assumes MOT would likely be high when doing construction through a busy intersection. See Master List of Items.
Construction Subtotal |  |  |  |  | 5445
Contingency | Percentage of Construction Subtotal |  |  | 40% | 2178 | Contingency would likely be high when doing construction through a busy intersection. See Master List of Items.
Construction Total |  |  |  |  | 7623
Design & Permitting | Percentage of Construction Costs |  |  | 20% | 1524.6 | 20% assumes reasonable contingency for design and permitting. See Master List of Items.
Total Project Costs for Design and Construction |  |  |  |  | 9100